## 📋 SEND CLIENT
PRODUCT CONTROL
2026-06-23 11:15
📦 TATA — ORDER DATA
Vulcan Order (PO) | Material | Designation |  | Order Date | ETA to TETE | Qty Ordered
4300034814 | 15643491 | HA 3128 | BRG BUSHING ADAPTER 125.41MM HA 3128 SKF | 2026-02-04 | 2026-06-08 | 4
4300034814 | 13040369 | COP.ATL160M | LABYRINTH SEAL 160MMATL TIMKEN | 2026-02-04 | 2026-06-08 | 2
4300034814 | 15153568 | COP.01EB180MGR | BALL BRNG 01 B 180MM GR COOPER | 2026-02-04 | 2026-06-08 | 2
0 | 15002466 | 6322/C3VL0241 | DEEP GROOVE BALL BEARING - INSOCOAT 6322 | 2026-02-03 | 2026-06-08 | 2
4300033496 | 15501296 | COP.01EB125MGR | CYL ROLL BRG 01 B 125M GR COOPER | 2025-12-23 | Read to Deliver | 1
4300033496 | 13188279 | COP.01EB180MGR | CL RL BRG 01 B 180M GR COOPER BEARINGS | 2025-12-23 | Read to Deliver | 3
0 | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-19 | 2026-09-03 | 1
0 | 13040555 | COP.02EB180MGR | CL RL BRG 02 B 180M GR COOPER BEARINGS | 2026-05-19 | 2026-09-03 | 5
0 | 13040555 | COP.02EB180MGR | CL RL BRG 02 B 180M GR COOPER BEARINGS | 2026-05-19 | 2026-09-03 | 2
0 | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-19 | 2026-09-03 | 1
4300037223 | 15134397 | SRV.NU 407 | CYL ROL BEARING | 2026-05-12 | 2026-08-20 | 3
4300037815 | 13040555 | COP.02EB180MGR | CYL ROLL BRG MSM180BR TIMKEN | 2026-05-12 | 2026-08-27 | 2
4300037815 | 13040485 | COP.02EB220MGR | CYL ROLL BRG MSM220BR TIMKEN | 2026-05-12 | 2026-08-27 | 1
4300037815 | 13040555 | COP.02EB180MGR | CYL ROLL BRG MSM180BR TIMKEN | 2026-05-12 | 2026-08-27 | 7
4300037815 | 15509234 | 70X110X10 HMSA10 RG | LIP SEAL FKM 70MM 110MM | 2026-05-12 | 2026-09-03 | 12
4300034374 | 15744967 | 24152 CC/W33 | BEARING 24152 CC/W33 SKF | 2026-04-01 | 2026-09-10 | 5
4300034374 | 15744967 | 24152 CC/W33 | BEARING 24152 CC/W33 SKF | 2026-04-01 | 2026-09-10 | 4
4300034374 | 15744967 | 24152 CC/W33 | BEARING 24152 CC/W33 SKF | 2026-04-01 | 2026-09-10 | 3
4300034374 | 15744967 | 24152 CC/W33 | BEARING 24152 CC/W33 SKF | 2026-04-01 | 2026-09-10 | 2
4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-07-08 | 7
4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-07-08 | 13
4300036353 | 13117942 | PHF TB4545X65MM | LCKG BUSH 65MM | 2026-03-19 | 2026-11-26 | 4
4300038759 | 15647107 | ASNH 526 | SIDE COVER ASNH 526 SKF | 2026-05-27 | 2026-06-17 | 2
4300038759 | 15647107 | ASNH 526 | SIDE COVER ASNH 526 SKF | 2026-05-27 | 2026-06-17 | 2
4300038759 | 15056552 | OH 3152 H | ADAPTER SLEEVE;OH 3152 H;SKF | 2026-05-27 | 2026-06-17 | 1
4300038759 | 15388676 | 22316 E/C3 | BEARING 22316 E C3 SKF | 2026-05-27 | 2026-06-17 | 1
4300038759 | 15062473 | H 318 | ADAPTER SLEEVE H 318 SKF | 2026-05-27 | 2026-06-17 | 3
4300038759 | 15647107 | ASNH 526 | SIDE COVER ASNH 526 SKF | 2026-05-27 | 2026-06-17 | 1
4300035325 | 15149626 | TU 50 TF | BEARING UNIT NON-LOC PASS SPLIT PED | 2026-02-13 | 2026-05-07 | 30
4300035325 | 15055683 | 22240 CC/W33 | BEARING 22240 CC/W33 SKF | 2026-02-13 | 2026-06-08 | 1
4300035325 | 15375665 | SNL 518-615 | PILLOW BLOCK NOD CI 80MM SNL 518-615 SKF | 2026-02-13 | 2026-07-09 | 5
4300035325 | 15351089 | 22218 EK | SPHERICAL ROLLER BEARING 22218 EK | 2026-02-13 | 2026-07-09 | 5
4300035325 | 0 | H 318 | ADAPTER SLEEVE H 318 SKF | 2026-02-13 | 2026-07-09 | 5
4300035325 | 13061642 | TXL 518 | SEAL TSN518 TK SKF | 2026-02-13 | 2026-07-09 | 5
4300035325 | 13065456 | FRB 12.5/160 | LOCATING RING FRB 12.5/160 | 2026-02-13 | 2026-07-09 | 10
4300034814 | 15375351 | 30230 | ROLL BEARING 30230 A FAG | 2026-02-04 | 2026-06-08 | 4
4300035325 | 15062560 | 23056 CCK/W33 | BEARING 23056 CCK/W33 SKF | 2026-02-13 | 2026-06-08 | 1
4300035325 | 15652160 | FRB 13/230 | RING FRB 13/230 SKF | 2026-02-13 | 2026-06-08 | 5
4300035325 | 15134397 | SRV.NU 407 | CYL ROL BEARING | 2026-02-13 | 2026-06-08 | 5
4300035325 | 15149497 | 32324 | ROLL BEARING 32324J2 SKF | 2026-02-13 | 2026-06-08 | 2
4300035325 | 15119748 | 23138 CCK/W33 | BEARING 23138 CC K W33 SKF | 2026-02-13 | 2026-06-08 | 1
4300035325 | 15505463 | 23140 CCK/W33 | BEARING 23140 CC K W33 SKF | 2026-02-13 | 2026-06-08 | 1
4300035325 | 15055683 | 22240 CC/W33 | BEARING 22240 CC/W33 SKF | 2026-02-13 | 2026-06-08 | 1
4300035558 | 15348604 | 6319/C3 | BALL BRNG 6319/C3 SKF | 2026-02-24 | 2026-06-08 | 4
4300035558 | 15383260 | NU 234 ECML/C3 | CL RL BRG NU 234 M C3 SKF | 2026-02-24 | 2026-06-08 | 4
4300035558 | 15383260 | NU 234 ECML/C3 | CL RL BRG NU 234 M C3 SKF | 2026-02-24 | 2026-06-08 | 3
4300035558 | 15153689 | COP.01EB150MGR | CL RL BRG 01 B 150M GR COPPER BEARINGS | 2026-02-24 | 2026-06-08 | 1
4300035558 | 15174197 | 6316/C3 | BALL BRNG 6316 C3 SKF | 2026-02-24 | 2026-06-08 | 2
4300035325 | 15392508 | 23232 CCK/W33 | BEARING 23232 CCK/W33 SKF | 2026-02-13 | 2026-06-08 | 1
4300035325 | 15130069 | 6216/C3 | BALL BRNG 6216 - C3 SKF | 2026-02-13 | 2026-06-08 | 1
4300035325 | 15003876 | 2217 K | BALL BRNG 2217 K SKF | 2026-02-13 | 2026-06-08 | 1
4300034374 | 15156479 | COP.01EB150MGR | CL RL BRG 01 B150M COOPER | 2026-04-01 | 2026-07-09 | 6
4300034374 | 15056773 | 32230 | BEARING;TAPERED ROLLER;32230JR;KOYO | 2026-04-01 | 2026-06-25 | 2
4300034374 | 15374830 | NU 2213 ECJ | CL RL BRG NU2213E SKF | 2026-04-01 | 2026-06-25 | 1
4300034374 | 13061642 | TXL 518 | SEAL TSN518 TK SKF | 2026-04-01 | 2026-06-25 | 19
4300034374 | 13037709 | FY 1.7/16 TF | BEARING UNIT SQUARE FLANGED | 2026-04-01 | 2026-06-25 | 1
4300036353 | 15047773 | H 3136 | BRG BUSHING FIXAT 160MM | 2026-03-19 | 2026-08-06 | 4
0 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-08-27 | 1
0 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-08-27 | 3
0 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-09-10 | 6
0 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-09-10 | 16
4300037783 | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-12 | 2026-08-27 | 1
4300037783 | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-12 | 2026-08-27 | 1
4300037815 | 15011261 | 22326 CCJA/W33VA405 | BEARING 22326 CC JA C4 W33 VA405 SKF | 2026-05-12 | 2026-08-20 | 60
4300037815 | 15011261 | 22326 CCJA/W33VA405 | BEARING 22326 CC JA C4 W33 VA405 SKF | 2026-05-12 | 2026-08-20 | 22
4300037947 | 15055565 | COP.SDQ3140 | BEARING;SANDVIK;01BC SD3140 GR TL | 2026-05-27 | 2026-06-17 | 3
0 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-08-13 | 6
0 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-08-13 | 6
0 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-08-13 | 4
0 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-08-13 | 6
0 | 15055680 | 22226 EK/C3 | BEARING 22226 CCK W33 SKF | 2026-05-19 | 2026-08-13 | 4
0 | 15419258 | H 3140 | BRG BUSHING FIXAT 180MM H 3140 SKF | 2026-05-19 | 2026-08-13 | 2
4300038759 | 13040483 | COP.ATL170M | LABYRINTH SEAL 170MMATL TIMKEN | 2026-05-27 | 2026-08-13 | 50
4300038759 | 17545471 | PHF TB5040X100MM | BUSH, TAPER LOCK;5040,100mm,101,6mm,SKF | 2026-05-27 | 2026-08-13 | 1
4300038759 | 13040483 | COP.ATL170M | LABYRINTH SEAL 170MMATL TIMKEN | 2026-05-27 | 2026-08-13 | 4
4300038759 | 17545471 | PHF TB5040X100MM | BUSH, TAPER LOCK;5040,100mm,101,6mm,SKF | 2026-05-27 | 2026-08-13 | 2
4300038547 | 17563131 | CMSS 943-LCI-SY-20M | CABLE ASSEMBLY; CMSS 943-LCI-SY-20M; SKF | 2026-05-21 | 2026-08-13 | 130
4300037223 | 15134397 | SRV.NU 407 | CYL ROL BEARING | 2026-05-12 | 2026-08-13 | 27
4300036353 | 15047773 | H 3136 | BRG BUSHING FIXAT 160MM | 2026-03-19 | 2026-08-06 | 4
4300035325 | 15153689 | COP.01EB150MGR | CL RL BRG 01 B 150M GR COPPER BEARINGS | 2026-02-13 | 2026-08-13 | 1
4300037815 | 15011261 | 22326 CCJA/W33VA405 | BEARING 22326 CC JA C4 W33 VA405 SKF | 2026-05-13 | 2026-06-24 | 20
0 | 0 | NU 2228 ECML/C3 | CYLINDRICAL ROLLER BEARING NU 2228 ECML/C3 | 2026-04-17 | 2026-05-05 | 4
4300036955 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-04-09 | 2026-07-02 | 4
4300036955 | 15004591 | 22328 CCJA/W33VA405 | BEARING 22328 CC JA C4 W33 VA405 SKF | 2026-04-09 | 2026-07-09 | 10
4300036955 | 17546207 | 6216-2Z/C3 | BEARING, BALL;DEEP GROOVE, 6216-2Z/C3,1 | 2026-04-09 | 2026-07-02 | 10
4300036955 | 15374646 | 31310/CL7C | ROLL BEARING 31310 J2 Q CL7C SKF | 2026-04-09 | 2026-07-02 | 10
4300036955 | 15374409 | 30314 | ROLL BEARING 30314 J2 Q SKF | 2026-04-09 | 2026-07-02 | 4
4300036955 | 15153017 | 6316/C3 | BEARING 6316-C3;FRAME 250S/M;WEG | 2026-04-09 | 2026-07-02 | 18
4300036955 | 17563152 | NU 319 ECJ/C3 | CYLIND ROLLER BEARING_NU_319_C3-SKF | 2026-04-09 | 2026-07-02 | 4
4300036955 | 15055680 | 22226 EK | BEARING 22226 CCK W33 SKF | 2026-04-09 | 2026-07-02 | 10
4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-06-25 | 33
4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-07-01 | 5
4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-06-26 | 20
4300036353 | 13048138 | 240X270X15 HMSA10 RG | LIP SEAL FKM 240MM 270MM | 2026-03-19 | 2026-06-11 | 4
4300036353 | 13119342 | PHF TB2517X50MM | LCKG BUSH 50MM | 2026-03-19 | 2026-07-23 | 4
4300036353 | 13120382 | PHF TB4545X80MM | LOCKING BUSH 80MM | 2026-03-19 | 2026-06-18 | 1
4300036353 | 13120382 | PHF TB4545X80MM | LOCKING BUSH 80MM | 2026-03-19 | 2026-07-23 | 3
4300036353 | 13048138 | 240X270X15 HMSA10 RG | LIP SEAL FKM 240MM 270MM | 2026-03-19 | 2026-06-11 | 4
4300036353 | 17544606 | 110X150X12 HMSA10 RG | OIL SEAL,110x150x12mm,110x150x12HMSA10RG | 2026-03-19 | 2026-06-11 | 20
4300036353 | 17546208 | 63X85X10 HMS5 RG | SEAL, OIL;63mm,85mm,10mm | 2026-03-19 | 2026-06-11 | 20
4300036353 | 15165110 | 140X170X12 HMSA10 RG | SEAL(RADIAL SHAFT) 140X170X12;BE275739 | 2026-03-19 | 2026-06-11 | 20
4300036353 | 17510665 | 118X150X12 HMS5 RG | FKM SEAL RETAINER 118MM 150MM | 2026-03-19 | 2026-07-16 | 20
4300036353 | 13051623 | 150X180X15 HMSA10 RG | LIP SEAL NBR 150MM 180MM | 2026-03-19 | 2026-06-11 | 20
4300036353 | 15173835 | 6304-2Z | BALL BRNG 6304 2Z WT C3 SKF | 2026-03-19 | 2026-06-11 | 30
4300036415 | 15077542 | 6022 | BALL BRNG 6022 SKF | 2026-03-19 | 2026-06-18 | 5
4300036415 | 13039801 | NU 2317 ECJ | CYL ROLL BRG NU2317C3 NTN | 2026-03-19 | 2026-06-18 | 10
4300036415 | 15134397 | SRV.NU 407 | CYL ROL BEARING | 2026-03-19 | 2026-06-18 | 20
4300036415 | 15355302 | 6034 M | BALL BRNG 6034 M SKF | 2026-03-19 | 2026-06-18 | 4
4300036415 | 15383260 | NU 234 ECML/C3 | CL RL BRG NU 234 M C3 SKF | 2026-03-19 | 2026-06-18 | 2
4300036415 | 15134394 | 22320 E/C3 | BEARING 22320 CC/W33 C3 SKF | 2026-03-19 | 2026-06-18 | 5
4300036415 | 15375665 | SNL 518-615 | PILLOW BLOCK NOD CI 80MM SNL 518-615 SKF | 2026-03-19 | 2026-06-11 | 1
4300034814 | 15377790 | 31315 | ROLL BEARING 31315 FAG | 2026-02-24 | 2026-06-08 | 4
4300035558 | 15125827 | SNL 520-617 | PILLOW BLOCK CI 90MM | 2026-02-24 | 2026-06-08 | 4
4300037783 | 15056773 | 32230 | BEARING;TAPERED ROLLER;32230JR;KOYO | 2026-05-12 | 2026-08-06 | 2
4300037783 | 15374646 | 31310/CL7C | ROLL BEARING 31310 J2 Q CL7C SKF | 2026-05-12 | 2026-08-06 | 6
4300037783 | 15374646 | 31310/CL7C | ROLL BEARING 31310 J2 Q CL7C SKF | 2026-05-12 | 2026-08-06 | 6
4300037223 | 15003876 | 2217 K | BALL BRNG 2217 K SKF | 2026-05-12 | 2026-08-06 | 1
4300037223 | 15383260 | NU 234 ECM/C3 | CL RL BRG NU 234 M C3 SKF | 2026-05-12 | 2026-08-06 | 5
4300037223 | 15055683 | 22240 CC/W33 | BEARING 22240 CC/W33 SKF | 2026-05-12 | 2026-08-06 | 8
4300037223 | 15501296 | COP.01EB125MGR | CYL ROLL BRG 01 B 125M GR COOPER | 2026-05-12 | 2026-08-06 | 1
4300037815 | 15419258 | H 3140 | BRG BUSHING FIXAT 180MM H 3140 SKF | 2026-05-12 | 2026-08-06 | 2
4300037815 | 17510662 | 70X90X10 HMSA10 RG | NBR SEAL RETAINER 70MM 90MM | 2026-05-12 | 2026-08-06 | 12
4300037815 | 15722015 | 32311 | ROLL BEARING 32311 SKF | 2026-05-12 | 2026-08-06 | 6
4300037815 | 13065480 | FRB 10/320 | LOCATING RING FRB 10/320 SKF | 2026-05-12 | 2026-08-06 | 8
0 | 0 | QJ 228 N2MA | ANGULAR CONTACT BALL BEARING QJ 228 N2MA | 2026-04-17 | 2026-07-16 | 2
4300036955 | 15004591 | 22328 CCJA/W33VA405 | BEARING 22328 CC JA C4 W33 VA405 SKF | 2026-04-09 | 2026-07-16 | 37
4300036955 | 15004591 | 22328 CCJA/W33VA405 | BEARING 22328 CC JA C4 W33 VA405 SKF | 2026-04-09 | 2026-07-16 | 33
4300036955 | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-04-09 | 2026-07-16 | 2
4300034374 | 15056773 | 32230 | BEARING;TAPERED ROLLER;32230JR;KOYO | 2026-04-01 | 2026-06-25 | 10
4300038547 | 17563131 | CMSS 943-LCI-SY-20M | CABLE ASSEMBLY; CMSS 943-LCI-SY-20M; SKF | 2026-05-21 | 2026-07-01 | 20
4300038547 | 17563129 | CMSS 942-LCI-SY-20M | CABLE ASSEMBLY; CMSS 942-LCT-SY-20M; SKF | 2026-05-21 | 2026-07-03 | 50
4300037783 | 15055680 | 22226 EK/C3 | BEARING 22226 CCK W33 SKF | 2026-05-12 | 2026-08-06 | 15
4300037783 | 15153017 | 6316/C3 | BEARING 6316-C3;FRAME 250S/M;WEG | 2026-05-12 | 2026-08-06 | 1
4300037783 | 15056773 | 32230 | BEARING;TAPERED ROLLER;32230JR;KOYO | 2026-05-12 | 2026-08-06 | 10
4300037783 | 15153017 | 6316/C3 | BEARING 6316-C3;FRAME 250S/M;WEG | 2026-05-12 | 2026-08-06 | 2

## 📋 ORDERS
📦 TATA — ORDER DATA
🔵 AZUL=preencha 🟢 VERDE=automático 🟣 ROXO=entrega cliente ➕ Copie linha para novos pedidos
Order Line | SKF Order | TATA Order | Vulcan Order (PO) | Material | Designation | Short Text | Order Date | Est. SKF Delivery Date | Warehouse | Qty Ordered | Qty Shipped | % Shipped | Unit Price | Line Total USD | Invoice No. | Status | Days to Delivery | Month/Year | Est. Customer Delivery Month | Qty Pending | Customer ID | SKF Collection Date | ✔ Delivered to Customer | Customer Delivery Date | Notes
0003A | 26Z0000099 | 252911949 | 4300034814 | 15643491 | HA 3128 | BRG BUSHING ADAPTER 125.41MM HA 3128 SKF | 2026-02-04 | 2026-04-15 | EMWH | 4 | 4 | 100% | 113.78 | 455.12 | 12568 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0005A | 26Z0000099 | 252911949 | 4300034814 | 13040369 | COP.ATL160M | LABYRINTH SEAL 160MMATL TIMKEN | 2026-02-04 | 2026-05-13 | EMWH | 2 | 2 | 100% | 266.66 | 533.32 | 12611 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0006A | 26Z0000099 | 252911949 | 4300034814 | 15153568 | COP.01EB180MGR | BALL BRNG 01 B 180MM GR COOPER | 2026-02-04 | 2026-05-27 | EMWH | 2 | 2 | 100% | 2441.75 | 4883.5 | 12660 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-11
0001A | 26Z0000097 | 252911950 |  | 15002466 | 6322/C3VL0241 | DEEP GROOVE BALL BEARING - INSOCOAT 6322 | 2026-02-03 | 2026-05-13 | EMWH | 2 | 2 | 100% | 915.85 | 1831.7 | 12612 | COLLECTED | 99 | 02/2026 | 06/2026 | 0 | F66050 | 2026-05-21 | ⚠ |  | Delivery on the 8.06.2026
0001A | 25Z0002759 | 252911760 | 4300033496 | 15501296 | COP.01EB125MGR | CYL ROLL BRG 01 B 125M GR COOPER | 2025-12-23 | 2026-03-04 | EMWH | 1 | 1 | 100% | 1048.88 | 1048.88 | 12403 | COLLECTED | ✔ OK | 12/2025 | OK | 0 | F66050 | 2026-04-16 | ✔ | 2026-06-18
0005A | 25Z0002759 | 252911760 | 4300033496 | 13188279 | COP.01EB180MGR | CL RL BRG 01 B 180M GR COOPER BEARINGS | 2025-12-23 | 2026-04-08 | EMWH | 3 | 3 | 100% | 2441.75 | 7325.25 | 12452 | COLLECTED | ✔ OK | 12/2025 | OK | 0 | F66050 | 2026-04-16 | ✔ | 2026-06-18
0001A | 26Z0000402 | 262910345 |  | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-19 | 2026-08-12 | EMWH | 1 | 1 | 100% | 1437.72 | 1437.72 | 0000000 | SHS | 85 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Expected delivery at SKF July 7
0005A | 26Z0000402 | 262910345 |  | 13040555 | COP.02EB180MGR | CL RL BRG 02 B 180M GR COOPER BEARINGS | 2026-05-19 | 2026-08-19 | EMWH | 5 | 5 | 100% | 4238.23 | 21191.15 | 0000000 | RPI | 92 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Expected delivery at SKF July 7
0006A | 26Z0000402 | 262910345 |  | 13040555 | COP.02EB180MGR | CL RL BRG 02 B 180M GR COOPER BEARINGS | 2026-05-19 | 2026-08-19 | EMWH | 2 | 2 | 100% | 4238.23 | 8476.46 | 0000000 | RPI | 92 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Expected delivery at SKF July 7
0009A | 26Z0000402 | 262910345 |  | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-19 | 2026-07-22 | EMWH | 1 | 1 | 100% | 1437.72 | 1437.72 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Expected delivery at SKF July 7
0002B | 26Z0000382 | 262910320 | 4300037223 | 15134397 | SRV.NU 407 | CYL ROL BEARING | 2026-05-12 | 2026-08-05 | EMWH | 3 | 0 | 0% | 71.7 | 215.1 | 0000000 | SHS | 85 | 05/2026 | 08/2026 | 3 | F66050 |  | ✘ |  | Requested from EDC dispatch date
0004A | 26Z0000383 | 262910319 | 4300037815 | 13040555 | COP.02EB180MGR | CYL ROLL BRG MSM180BR TIMKEN | 2026-05-12 | 2026-08-12 | EMWH | 2 | 2 | 100% | 4395.2 | 8790.4 | 0000000 | SHS | 92 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Requested for improved production
0005A | 26Z0000383 | 262910319 | 4300037815 | 13040485 | COP.02EB220MGR | CYL ROLL BRG MSM220BR TIMKEN | 2026-05-12 | 2026-08-12 | EMWH | 1 | 1 | 100% | 10786.44 | 10786.44 | 0000000 | SHS | 92 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Requested for improved production
0006A | 26Z0000383 | 262910319 | 4300037815 | 13040555 | COP.02EB180MGR | CYL ROLL BRG MSM180BR TIMKEN | 2026-05-12 | 2026-08-12 | EMWH | 7 | 7 | 100% | 4395.2 | 30766.4 | 0000000 | SHS | 92 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Requested for improved production
0007A | 26Z0000383 | 262910319 | 4300037815 | 15509234 | 70X110X10 HMSA10 RG | LIP SEAL FKM 70MM 110MM | 2026-05-12 | 2026-08-05 | EMWH | 12 | 12 | 100% | 2.71 | 32.52 | 0000000 | SHS | 85 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | 25.06.2026 ETA - SANR0409719
0002A | 26Z0000279 | 252912134 | 4300034374 | 15744967 | 24152 CC/W33 | BEARING 24152 CC/W33 SKF | 2026-04-01 | 2026-07-22 | EMWH | 5 | 0 | 0% | 2589.33 | 12946.65 | 0000000 | RPI | 112 | 04/2026 | 08/2026 | 5 | F66050 | 2026-06-03 | 🔮 |  | Request to order directly from factory - Cephas to change order
0002B | 26Z0000279 | 252912134 | 4300034374 | 15744967 | 24152 CC/W33 | BEARING 24152 CC/W33 SKF | 2026-04-01 | 2026-07-22 | EMWH | 4 | 0 | 0% | 2589.33 | 10357.32 | 0000000 | RPI | 112 | 04/2026 | 08/2026 | 4 | F66050 | 2026-06-03 | 🔮 |  | Request to order directly from factory - Cephas to change order
0002C | 26Z0000279 | 252912134 | 4300034374 | 15744967 | 24152 CC/W33 | BEARING 24152 CC/W33 SKF | 2026-04-01 | 2026-07-22 | EMWH | 3 | 0 | 0% | 2589.33 | 7767.99 | 0000000 | RPI | 112 | 04/2026 | 08/2026 | 3 | F66050 | 2026-06-03 | 🔮 |  | Request to order directly from factory - Cephas to change order
0007A | 26Z0000279 | 252912134 | 4300034374 | 15744967 | 24152 CC/W33 | BEARING 24152 CC/W33 SKF | 2026-04-01 | 2026-07-22 | EMWH | 2 | 0 | 0% | 2589.33 | 5178.66 | 0000000 | RPI | 112 | 04/2026 | 08/2026 | 2 | F66050 | 2026-06-03 | 🔮 |  | Request to order directly from factory - Cephas to change order
0002C | 26Z0000280 | 262910001 | 4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-07-02 | EMWH | 7 | 7 | 100% | 495 | 3465 | 0000000 | SHS | 92 | 04/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | Requested for production improvement , no global availability
0003A | 26Z0000280 | 262910001 | 4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-07-02 | EMWH | 13 | 13 | 100% | 495 | 6435 | 0000000 | SHS | 92 | 04/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | Requested for production improvement , no global availability
0002B | 26Z0000240 | 252912296 | 4300036353 | 13117942 | PHF TB4545X65MM | LCKG BUSH 65MM | 2026-03-19 | 2026-11-18 | EMWH | 4 | 4 | 100% | 60.21 | 240.84 | 0000000 | RBK | 244 | 03/2026 | 12/2026 | 0 | F66050 |  | ✘ |  | Awaiting improvement from Factory
0001A | 26Z0000428 | 262910449 | 4300038759 | 15647107 | ASNH 526 | SIDE COVER ASNH 526 SKF | 2026-05-27 | 2026-06-02 | QZSS | 2 | 2 | 100% | 5.54 | 11.08 | 12765 | READY FOR COLLECTION | 6 | 05/2026 | 06/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0002A | 26Z0000428 | 262910449 | 4300038759 | 15647107 | ASNH 526 | SIDE COVER ASNH 526 SKF | 2026-05-27 | 2026-06-02 | QZSS | 2 | 2 | 100% | 5.54 | 11.08 | 12765 | READY FOR COLLECTION | 6 | 05/2026 | 06/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0006A | 26Z0000428 | 262910449 | 4300038759 | 15056552 | OH 3152 H | ADAPTER SLEEVE;OH 3152 H;SKF | 2026-05-27 | 2026-06-02 | QZSS | 1 | 1 | 100% | 601.87 | 601.87 | 12765 | READY FOR COLLECTION | 6 | 05/2026 | 06/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0008A | 26Z0000428 | 262910449 | 4300038759 | 15388676 | 22316 E/C3 | BEARING 22316 E C3 SKF | 2026-05-27 | 2026-06-02 | QZSS | 1 | 1 | 100% | 146.04 | 146.04 | 12765 | READY FOR COLLECTION | 6 | 05/2026 | 06/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0009A | 26Z0000428 | 262910449 | 4300038759 | 15062473 | H 318 | ADAPTER SLEEVE H 318 SKF | 2026-05-27 | 2026-06-02 | QZSS | 3 | 3 | 100% | 31.31 | 93.93 | 12765 | READY FOR COLLECTION | 6 | 05/2026 | 06/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0010A | 26Z0000428 | 262910449 | 4300038759 | 15647107 | ASNH 526 | SIDE COVER ASNH 526 SKF | 2026-05-27 | 2026-06-02 | QZSS | 1 | 1 | 100% | 5.54 | 5.54 | 12765 | READY FOR COLLECTION | 6 | 05/2026 | 06/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0011A | 26Z0000126 | 252911981 | 4300035325 | 15149626 | TU 50 TF | BEARING UNIT NON-LOC PASS SPLIT PED | 2026-02-13 | 2026-04-22 | EMWH | 30 | 30 | 100% | 39.33 | 1179.9 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0013A | 26Z0000126 | 252911981 | 4300035325 | 15055683 | 22240 CC/W33 | BEARING 22240 CC/W33 SKF | 2026-02-13 | 2026-05-06 | EMWH | 1 | 1 | 100% | 1044.34 | 1044.34 | 12632 | COLLECTED | 82 | 02/2026 | 05/2026 | 0 | F66050 | 2026-05-21 | ⚠ |  | Delivery on the 8.06.2026
0014A | 26Z0000126 | 252911981 | 4300035325 | 15375665 | SNL 518-615 | PILLOW BLOCK NOD CI 80MM SNL 518-615 SKF | 2026-02-13 | 2026-06-24 | EMWH | 5 | 5 | 100% | 110.25 | 551.25 | 12723 | READY FOR COLLECTION | 131 | 02/2026 | 07/2026 | 0 | F66050 | 2026-06-02 | 🔮
0015A | 26Z0000126 | 252911981 | 4300035325 | 15351089 | 22218 EK | SPHERICAL ROLLER BEARING 22218 EK | 2026-02-13 | 2026-06-24 | EMWH | 5 | 5 | 100% | 108.14 | 540.7 | 12723 | READY FOR COLLECTION | 131 | 02/2026 | 07/2026 | 0 | F66050 | 2026-06-02 | 🔮
0016A | 26Z0000126 | 252911981 | 4300035325 |  | H 318 | ADAPTER SLEEVE H 318 SKF | 2026-02-13 | 2026-06-24 | EMWH | 5 | 5 | 100% | 25.74 | 128.7 | 12723 | READY FOR COLLECTION | 131 | 02/2026 | 07/2026 | 0 | F66050 | 2026-06-02 | 🔮
0017A | 26Z0000126 | 252911981 | 4300035325 | 13061642 | TXL 518 | SEAL TSN518 TK SKF | 2026-02-13 | 2026-06-24 | EMWH | 5 | 5 | 100% | 4.79 | 23.95 | 12723 | READY FOR COLLECTION | 131 | 02/2026 | 07/2026 | 0 | F66050 | 2026-06-02 | 🔮
0018A | 26Z0000126 | 252911981 | 4300035325 | 13065456 | FRB 12.5/160 | LOCATING RING FRB 12.5/160 | 2026-02-13 | 2026-06-24 | EMWH | 10 | 10 | 100% | 3.35 | 33.5 | 12723 | READY FOR COLLECTION | 131 | 02/2026 | 07/2026 | 0 | F66050 | 2026-06-02 | 🔮
0002A | 26Z0000099 | 252911949 | 4300034814 | 15375351 | 30230 | ROLL BEARING 30230 A FAG | 2026-02-04 | 2026-04-15 | EMWH | 4 | 4 | 100% | 419.07 | 1676.28 | 12568 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0004A | 26Z0000126 | 252911981 | 4300035325 | 15062560 | 23056 CCK/W33 | BEARING 23056 CCK/W33 SKF | 2026-02-13 | 2026-04-22 | EMWH | 1 | 1 | 100% | 1455.7 | 1455.7 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0005A | 26Z0000126 | 252911981 | 4300035325 | 15652160 | FRB 13/230 | RING FRB 13/230 SKF | 2026-02-13 | 2026-04-22 | EMWH | 5 | 5 | 100% | 7.56 | 37.8 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0006B | 26Z0000126 | 252911981 | 4300035325 | 15134397 | SRV.NU 407 | CYL ROL BEARING | 2026-02-13 | 2026-05-06 | EMWH | 5 | 5 | 100% | 69.69 | 348.45 | 12632 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0007A | 26Z0000126 | 252911981 | 4300035325 | 15149497 | 32324 | ROLL BEARING 32324J2 SKF | 2026-02-13 | 2026-04-22 | EMWH | 2 | 2 | 100% | 712.12 | 1424.24 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0008A | 26Z0000126 | 252911981 | 4300035325 | 15119748 | 23138 CCK/W33 | BEARING 23138 CC K W33 SKF | 2026-02-13 | 2026-04-22 | EMWH | 1 | 1 | 100% | 853.39 | 853.39 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0009A | 26Z0000126 | 252911981 | 4300035325 | 15505463 | 23140 CCK/W33 | BEARING 23140 CC K W33 SKF | 2026-02-13 | 2026-04-22 | EMWH | 1 | 1 | 100% | 1056.59 | 1056.59 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0010A | 26Z0000126 | 252911981 | 4300035325 | 15055683 | 22240 CC/W33 | BEARING 22240 CC/W33 SKF | 2026-02-13 | 2026-04-22 | EMWH | 1 | 1 | 100% | 1044.34 | 1044.34 | 12545 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-04-20 | ✔ | 2026-06-08
0002A | 26Z0000174 | 252912114 | 4300035558 | 15348604 | 6319/C3 | BALL BRNG 6319/C3 SKF | 2026-02-24 | 2026-05-06 | EMWH | 4 | 4 | 100% | 95.8 | 383.2 | 12622 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0003A | 26Z0000174 | 252912114 | 4300035558 | 15383260 | NU 234 ECML/C3 | CL RL BRG NU 234 M C3 SKF | 2026-02-24 | 2026-05-13 | EMWH | 4 | 4 | 100% | 730.28 | 2921.12 | 12622 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0003B | 26Z0000174 | 252912114 | 4300035558 | 15383260 | NU 234 ECML/C3 | CL RL BRG NU 234 M C3 SKF | 2026-02-24 | 2026-05-13 | EMWH | 3 | 3 | 100% | 730.28 | 2190.84 | 12622 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0004A | 26Z0000174 | 252912114 | 4300035558 | 15153689 | COP.01EB150MGR | CL RL BRG 01 B 150M GR COPPER BEARINGS | 2026-02-24 | 2026-05-27 | EMWH | 1 | 1 | 100% | 1379.51 | 1379.51 | 12661 | COLLECTED | 92 | 02/2026 | 06/2026 | 0 | F66050 | 2026-05-21 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0005A | 26Z0000174 | 252912114 | 4300035558 | 15174197 | 6316/C3 | BALL BRNG 6316 C3 SKF | 2026-02-24 | 2026-02-27 | QZSS | 2 | 2 | 100% | 51.82 | 103.64 | 12431 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-04-16 | ✔ | 2026-06-22
0001A | 26Z0000126 | 252911981 | 4300035325 | 15392508 | 23232 CCK/W33 | BEARING 23232 CCK/W33 SKF | 2026-02-13 | 2026-04-22 | EMWH | 1 | 1 | 100% | 659.88 | 659.88 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0002A | 26Z0000126 | 252911981 | 4300035325 | 15130069 | 6216/C3 | BALL BRNG 6216 - C3 SKF | 2026-02-13 | 2026-04-22 | EMWH | 1 | 1 | 100% | 30.44 | 30.44 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0003A | 26Z0000126 | 252911981 | 4300035325 | 15003876 | 2217 K | BALL BRNG 2217 K SKF | 2026-02-13 | 2026-04-22 | EMWH | 1 | 1 | 100% | 120.38 | 120.38 | 12545 | COLLECTED | 68 | 02/2026 | 05/2026 | 0 | F66050 | 2026-04-20 | ⚠ |  | Gate Pass Issue (Still it is in TATA Stock)
0003A | 26Z0000279 | 252912134 | 4300034374 | 15156479 | COP.01EB150MGR | CL RL BRG 01 B150M COOPER | 2026-04-01 | 2026-06-24 | EMWH | 6 | 6 | 100% | 1241.56 | 7449.36 | 12755 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0004A | 26Z0000279 | 252912134 | 4300034374 | 15056773 | 32230 | BEARING;TAPERED ROLLER;32230JR;KOYO | 2026-04-01 | 2026-06-10 | EMWH | 2 | 2 | 100% | 478.59 | 957.18 | 12755 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0005A | 26Z0000279 | 252912134 | 4300034374 | 15374830 | NU 2213 ECJ | CL RL BRG NU2213E SKF | 2026-04-01 | 2026-06-10 | EMWH | 1 | 1 | 100% | 54.47 | 54.47 | 12755 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0006A | 26Z0000279 | 252912134 | 4300034374 | 13061642 | TXL 518 | SEAL TSN518 TK SKF | 2026-04-01 | 2026-06-10 | EMWH | 19 | 19 | 100% | 7.65 | 145.35 | 12755 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0008A | 26Z0000279 | 252912134 | 4300034374 | 13037709 | FY 1.7/16 TF | BEARING UNIT SQUARE FLANGED | 2026-04-01 | 2026-06-10 | EMWH | 1 | 1 | 100% | 21.67 | 21.67 | 12755 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0013A | 26Z0000240 | 252912296 | 4300036353 | 15047773 | H 3136 | BRG BUSHING FIXAT 160MM | 2026-03-19 | 2026-07-22 | EMWH | 4 | 4 | 100% | 186.13 | 744.52 | 0000000 | SHS | 125 | 03/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | 25.06.2026 ETA - SANR0409719
0004B | 26Z0000402 | 262910345 |  | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-07-22 | EMWH | 1 | 1 | 100% | 112.33 | 112.33 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Checking if factory can assist with stock
0004C | 26Z0000402 | 262910345 |  | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-07-22 | EMWH | 3 | 3 | 100% | 112.33 | 336.99 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Checking if factory can assist with stock
0004D | 26Z0000402 | 262910345 |  | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-08-26 | EMWH | 6 | 6 | 100% | 112.33 | 673.98 | 0000000 | RPI | 99 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Checking if factory can assist with stock
0007A | 26Z0000402 | 262910345 |  | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-08-26 | EMWH | 16 | 16 | 100% | 112.33 | 1797.28 | 0000000 | RPI | 99 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Checking if factory can assist with stock
0002A | 26Z0000381 | 262910321 | 4300037783 | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-12 | 2026-08-12 | EMWH | 1 | 1 | 100% | 1490.97 | 1490.97 | 0000000 | SHS | 92 | 05/2026 | 09/2026 | 0 | F66050 |  | ✘ |  | Stock shipped from EDC - Awaiting shipping details
0008A | 26Z0000381 | 262910321 | 4300037783 | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-12 | 2026-06-22 | EMWH | 1 | 1 | 100% | 1490.97 | 1490.97 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | Stock shipped from EDC - Awaiting shipping details
0001A | 26Z0000383 | 262910319 | 4300037815 | 15011261 | 22326 CCJA/W33VA405 | BEARING 22326 CC JA C4 W33 VA405 SKF | 2026-05-12 | 2026-07-22 | EMWH | 60 | 60 | 100% | 678.04 | 40682.4 | 0000000 | SHS | 71 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Stock is in RPI in Belguim , will be shipped out this week
0003A | 26Z0000383 | 262910319 | 4300037815 | 15011261 | 22326 CCJA/W33VA405 | BEARING 22326 CC JA C4 W33 VA405 SKF | 2026-05-12 | 2026-07-22 | EMWH | 22 | 22 | 100% | 678.04 | 14916.88 | 0000000 | SHS | 71 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Stock is in RPI in Belguim , will be shipped out this week
0001A | 26Z0000422 | 262910469 | 4300037947 | 15055565 | COP.SDQ3140 | BEARING;SANDVIK;01BC SD3140 GR TL | 2026-05-27 | 2026-06-02 | QZSS | 3 | 0 | 0% | 3267.67 | 9803.01 | 0000000 | RPI | 6 | 05/2026 | 06/2026 | 3 | F66050 |  | 🔮 |  | 26L0024238 / LOCAL
0002A | 26Z0000402 | 262910345 |  | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-07-22 | EMWH | 6 | 6 | 100% | 112.33 | 673.98 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Will be shipped out today , awaiting shipment details
0002B | 26Z0000402 | 262910345 |  | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-07-22 | EMWH | 6 | 6 | 100% | 112.33 | 673.98 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Will be shipped out today , awaiting shipment details
0003A | 26Z0000402 | 262910345 |  | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-07-22 | EMWH | 4 | 4 | 100% | 112.33 | 449.32 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Will be shipped out today , awaiting shipment details
0004A | 26Z0000402 | 262910345 |  | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-05-19 | 2026-07-22 | EMWH | 6 | 6 | 100% | 112.33 | 673.98 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Will be shipped out today , awaiting shipment details
0008A | 26Z0000402 | 262910345 |  | 15055680 | 22226 EK/C3 | BEARING 22226 CCK W33 SKF | 2026-05-19 | 2026-07-22 | EMWH | 4 | 4 | 100% | 297.43 | 1189.72 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Will be shipped out today , awaiting shipment details
0010A | 26Z0000402 | 262910345 |  | 15419258 | H 3140 | BRG BUSHING FIXAT 180MM H 3140 SKF | 2026-05-19 | 2026-07-22 | EMWH | 2 | 2 | 100% | 194.06 | 388.12 | 0000000 | SHS | 64 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | Will be shipped out today , awaiting shipment details
0003A | 26Z0000428 | 262910449 | 4300038759 | 13040483 | COP.ATL170M | LABYRINTH SEAL 170MMATL TIMKEN | 2026-05-27 | 2026-09-23 | EMWH | 50 | 50 | 100% | 226.14 | 11307 | 0000000 | RBK | 119 | 05/2026 | 10/2026 | 0 | F66050 |  | ✘ |  | Requested for availability USA
0004B | 26Z0000428 | 262910449 | 4300038759 | 17545471 | PHF TB5040X100MM | BUSH, TAPER LOCK;5040,100mm,101,6mm,SKF | 2026-05-27 | 2027-01-20 | EMWH | 1 | 1 | 100% | 86.1 | 86.1 | 0000000 | BOK | 238 | 05/2026 | 02/2027 | 0 | F66050 |  | ✘ |  | No Availability - Reached out to factory
0005A | 26Z0000428 | 262910449 | 4300038759 | 13040483 | COP.ATL170M | LABYRINTH SEAL 170MMATL TIMKEN | 2026-05-27 | 2026-09-23 | EMWH | 4 | 4 | 100% | 226.14 | 904.56 | 0000000 | RBK | 119 | 05/2026 | 10/2026 | 0 | F66050 |  | ✘ |  | Requested for availability USA
0007A | 26Z0000428 | 262910449 | 4300038759 | 17545471 | PHF TB5040X100MM | BUSH, TAPER LOCK;5040,100mm,101,6mm,SKF | 2026-05-27 | 2027-01-20 | EMWH | 2 | 2 | 100% | 86.1 | 172.2 | 0000000 | BOK | 238 | 05/2026 | 02/2027 | 0 | F66050 |  | ✘ |  | No Availability - Reached out to factory
0001A | 26Z0000410 | 262910450 | 4300038547 | 17563131 | CMSS 943-LCI-SY-20M | CABLE ASSEMBLY; CMSS 943-LCI-SY-20M; SKF | 2026-05-21 | 2026-07-22 | EMWH | 130 | 130 | 100% | 192.03 | 24963.9 | 0000000 | RBK | 62 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | No stock availability - Current ETA 04.08.2026 - Requested for improvement
0002A | 26Z0000382 | 262910320 | 4300037223 | 15134397 | SRV.NU 407 | CYL ROL BEARING | 2026-05-12 |  | EMWH | 27 | 0 | 0% | 71.7 | 1935.9 | 0000000 | ENT | TBA | 05/2026 |  | 27 | F66050 |  | ✘ |  | No stock availability - Requested for factory acknowledgement
0005A | 26Z0000240 | 252912296 | 4300036353 | 15047773 | H 3136 | BRG BUSHING FIXAT 160MM | 2026-03-19 | 2026-08-03 | QZSS | 4 | 4 | 100% | 0 | 0 | 0000000 | BOK | 137 | 03/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | EDC has stock requested for confirmation
0019A | 26Z0000126 | 252911981 | 4300035325 | 15153689 | COP.01EB150MGR | CL RL BRG 01 B 150M GR COPPER BEARINGS | 2026-02-13 |  | EMWH | 1 |  | 0% | 1403.53 | 1403.53 | 0000000 | ENT | TBA | 02/2026 |  | 1 | F66050 |  | ✘ |  | No global availability - Requested for confirmation
0001A | 26Z0000386 | 262910319A | 4300037815 | 15011261 | 22326 CCJA/W33VA405 | BEARING 22326 CC JA C4 W33 VA405 SKF | 2026-05-13 | 2026-06-09 | EMWH | 20 | 20 | 100% | 678.04 | 13560.8 | 12675 | COLLECTED | ✔ OK | 05/2026 | OK | 0 | F66050 | 2026-05-22 | ✔ | 2026-06-08
0002A | 26Z0000304 | 262910137 |  |  | NU 2228 ECML/C3 | CYLINDRICAL ROLLER BEARING NU 2228 ECML/C3 | 2026-04-17 | 2026-04-20 | QZSS | 4 | 4 | 100% | 570.15 | 2280.6 | 12562 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-04-20 | ✔ | 2026-04-28
0001A | 26Z0000291 | 262910021 | 4300036955 | 16177612 | TSN 526 S | SEAL TSN526S SKF | 2026-04-09 | 2026-06-17 | EMWH | 4 | 4 | 100% | 113.22 | 452.88 | 12720 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0002B | 26Z0000291 | 262910021 | 4300036955 | 15004591 | 22328 CCJA/W33VA405 | BEARING 22328 CC JA C4 W33 VA405 SKF | 2026-04-09 | 2026-06-24 | EMWH | 10 | 10 | 100% | 838.97 | 8389.7 | 12720 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0003A | 26Z0000291 | 262910021 | 4300036955 | 17546207 | 6216-2Z/C3 | BEARING, BALL;DEEP GROOVE, 6216-2Z/C3,1 | 2026-04-09 | 2026-06-17 | EMWH | 10 | 10 | 100% | 20.2 | 202 | 12720 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0004A | 26Z0000291 | 262910021 | 4300036955 | 15374646 | 31310/CL7C | ROLL BEARING 31310 J2 Q CL7C SKF | 2026-04-09 | 2026-06-17 | TBEW | 10 | 10 | 100% | 35.31 | 353.1 | 12720 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0005A | 26Z0000291 | 262910021 | 4300036955 | 15374409 | 30314 | ROLL BEARING 30314 J2 Q SKF | 2026-04-09 | 2026-06-17 | TBEW | 4 | 4 | 100% | 33.17 | 132.68 | 12720 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0006A | 26Z0000291 | 262910021 | 4300036955 | 15153017 | 6316/C3 | BEARING 6316-C3;FRAME 250S/M;WEG | 2026-04-09 | 2026-06-17 | EMWH | 18 | 18 | 100% | 40.4 | 727.2 | 12720 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0007A | 26Z0000291 | 262910021 | 4300036955 | 17563152 | NU 319 ECJ/C3 | CYLIND ROLLER BEARING_NU_319_C3-SKF | 2026-04-09 | 2026-06-17 | EMWH | 4 | 4 | 100% | 136.16 | 544.64 | 12720 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0008A | 26Z0000291 | 262910021 | 4300036955 | 15055680 | 22226 EK | BEARING 22226 CCK W33 SKF | 2026-04-09 | 2026-06-17 | EMWH | 10 | 10 | 100% | 299.81 | 2998.1 | 12720 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0002A | 26Z0000280 | 262910001 | 4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-06-10 | EMWH | 33 | 33 | 100% | 495 | 16335 | 12610 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0002B | 26Z0000280 | 262910001 | 4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-06-16 | EMWH | 5 | 5 | 100% | 495 | 2475 | 12679 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0003B | 26Z0000280 | 262910001 | 4300036757 | 15475312 | CMPT 2310TX20 | SENSOR INTEGRATED CABLE; CMPT 2310TX20 | 2026-04-01 | 2026-06-11 | EMWH | 20 | 20 | 100% | 495 | 9900 | 12679 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0001A | 26Z0000240 | 252912296 | 4300036353 | 13048138 | 240X270X15 HMSA10 RG | LIP SEAL FKM 240MM 270MM | 2026-03-19 | 2026-05-27 | EMWH | 4 | 4 | 100% | 23.88 | 95.52 | 12643 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-22
0003A | 26Z0000240 | 252912296 | 4300036353 | 13119342 | PHF TB2517X50MM | LCKG BUSH 50MM | 2026-03-19 | 2026-07-08 | EMWH | 4 | 4 | 100% | 7.95 | 31.8 | 12643 | COLLECTED | 111 | 03/2026 | 07/2026 | 0 | F66050 | 2026-05-21 | ⚠ |  | Still waiting for Transporter & SKF to confirm the ETA and Material details.
0004A | 26Z0000240 | 252912296 | 4300036353 | 13120382 | PHF TB4545X80MM | LOCKING BUSH 80MM | 2026-03-19 | 2026-06-03 | EMWH | 1 | 1 | 100% | 49.96 | 49.96 | 12643 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-22
0004B | 26Z0000240 | 252912296 | 4300036353 | 13120382 | PHF TB4545X80MM | LOCKING BUSH 80MM | 2026-03-19 | 2026-07-08 | EMWH | 3 | 3 | 100% | 49.96 | 149.88 | 12643 | COLLECTED | 111 | 03/2026 | 07/2026 | 0 | F66050 | 2026-05-21 | ⚠ |  | Still waiting for Transporter & SKF to confirm the ETA and Material details.
0006A | 26Z0000240 | 252912296 | 4300036353 | 13048138 | 240X270X15 HMSA10 RG | LIP SEAL FKM 240MM 270MM | 2026-03-19 | 2026-05-27 | EMWH | 4 | 4 | 100% | 23.88 | 95.52 | 12643 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-22
0007A | 26Z0000240 | 252912296 | 4300036353 | 17544606 | 110X150X12 HMSA10 RG | OIL SEAL,110x150x12mm,110x150x12HMSA10RG | 2026-03-19 | 2026-05-27 | EMWH | 20 | 20 | 100% | 4.5 | 90 | 12643 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-22
0008A | 26Z0000240 | 252912296 | 4300036353 | 17546208 | 63X85X10 HMS5 RG | SEAL, OIL;63mm,85mm,10mm | 2026-03-19 | 2026-05-27 | EMWH | 20 | 20 | 100% | 1.55 | 31 | 12643 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-22
0009A | 26Z0000240 | 252912296 | 4300036353 | 15165110 | 140X170X12 HMSA10 RG | SEAL(RADIAL SHAFT) 140X170X12;BE275739 | 2026-03-19 | 2026-05-27 | EMWH | 20 | 20 | 100% | 5.69 | 113.8 | 12643 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-22
0010A | 26Z0000240 | 252912296 | 4300036353 | 17510665 | 118X150X12 HMS5 RG | FKM SEAL RETAINER 118MM 150MM | 2026-03-19 | 2026-07-01 | EMWH | 20 | 20 | 100% | 4.5 | 90 | 12643 | COLLECTED | 104 | 03/2026 | 07/2026 | 0 | F66050 | 2026-05-21 | ⚠ |  | Still waiting for Transporter & SKF to confirm the ETA and Material details.
0011A | 26Z0000240 | 252912296 | 4300036353 | 13051623 | 150X180X15 HMSA10 RG | LIP SEAL NBR 150MM 180MM | 2026-03-19 | 2026-05-27 | EMWH | 20 | 20 | 100% | 6.04 | 120.8 | 12643 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-22
0012A | 26Z0000240 | 252912296 | 4300036353 | 15173835 | 6304-2Z | BALL BRNG 6304 2Z WT C3 SKF | 2026-03-19 | 2026-05-27 | EMWH | 30 | 30 | 100% | 2.82 | 84.6 | 12643 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-22
0001A | 26Z0000242 | 252912295 | 4300036415 | 15077542 | 6022 | BALL BRNG 6022 SKF | 2026-03-19 | 2026-06-03 | EMWH | 5 | 5 | 100% | 48.44 | 242.2 | 12721 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0002A | 26Z0000242 | 252912295 | 4300036415 | 13039801 | NU 2317 ECJ | CYL ROLL BRG NU2317C3 NTN | 2026-03-19 | 2026-06-03 | II01 | 10 | 10 | 100% | 364.08 | 3640.8 | 12721 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0003B | 26Z0000242 | 252912295 | 4300036415 | 15134397 | SRV.NU 407 | CYL ROL BEARING | 2026-03-19 | 2026-06-03 | EMWH | 20 | 20 | 100% | 69.69 | 1393.8 | 12721 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0004A | 26Z0000242 | 252912295 | 4300036415 | 15355302 | 6034 M | BALL BRNG 6034 M SKF | 2026-03-19 | 2026-06-03 | EMWH | 4 | 4 | 100% | 260.55 | 1042.2 | 12721 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0005A | 26Z0000242 | 252912295 | 4300036415 | 15383260 | NU 234 ECML/C3 | CL RL BRG NU 234 M C3 SKF | 2026-03-19 | 2026-06-03 | EMWH | 2 | 2 | 100% | 657.44 | 1314.88 | 12721 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0006A | 26Z0000242 | 252912295 | 4300036415 | 15134394 | 22320 E/C3 | BEARING 22320 CC/W33 C3 SKF | 2026-03-19 | 2026-06-03 | EMWH | 5 | 5 | 100% | 276.87 | 1384.35 | 12721 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0007A | 26Z0000242 | 252912295 | 4300036415 | 15375665 | SNL 518-615 | PILLOW BLOCK NOD CI 80MM SNL 518-615 SKF | 2026-03-19 | 2026-05-27 | QZSS | 1 | 1 | 100% | 102.4 | 102.4 | 12722 | COLLECTED | ✔ OK | 03/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0001A | 26Z0000170 | 252911949 | 4300034814 | 15377790 | 31315 | ROLL BEARING 31315 FAG | 2026-02-24 | 2026-05-13 | TBEW | 4 | 4 | 100% | 78.83 | 315.32 | 12613 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0001A | 26Z0000174 | 252912114 | 4300035558 | 15125827 | SNL 520-617 | PILLOW BLOCK CI 90MM | 2026-02-24 | 2026-05-06 | EMWH | 4 | 4 | 100% | 123.9 | 495.6 | 12622 | COLLECTED | ✔ OK | 02/2026 | OK | 0 | F66050 | 2026-05-21 | ✔ | 2026-06-08
0010A | 26Z0000381 | 262910321 | 4300037783 | 15056773 | 32230 | BEARING;TAPERED ROLLER;32230JR;KOYO | 2026-05-12 | 2026-06-22 | EMWH | 2 | 2 | 100% | 492.38 | 984.76 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0013A | 26Z0000381 | 262910321 | 4300037783 | 15374646 | 31310/CL7C | ROLL BEARING 31310 J2 Q CL7C SKF | 2026-05-12 | 2026-06-22 | TBEW | 6 | 6 | 100% | 36.33 | 217.98 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 - ETA - SANR0409719
0014A | 26Z0000381 | 262910321 | 4300037783 | 15374646 | 31310/CL7C | ROLL BEARING 31310 J2 Q CL7C SKF | 2026-05-12 | 2026-06-22 | TBEW | 6 | 6 | 100% | 36.33 | 217.98 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 - ETA - SANR0409719
0001A | 26Z0000382 | 262910320 | 4300037223 | 15003876 | 2217 K | BALL BRNG 2217 K SKF | 2026-05-12 | 2026-06-22 | EMWH | 1 | 1 | 100% | 123.84 | 123.84 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0003A | 26Z0000382 | 262910320 | 4300037223 | 15383260 | NU 234 ECM/C3 | CL RL BRG NU 234 M C3 SKF | 2026-05-12 | 2026-06-22 | EMWH | 5 | 5 | 100% | 676.38 | 3381.9 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0004A | 26Z0000382 | 262910320 | 4300037223 | 15055683 | 22240 CC/W33 | BEARING 22240 CC/W33 SKF | 2026-05-12 | 2026-06-22 | EMWH | 8 | 8 | 100% | 993.02 | 7944.16 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0005A | 26Z0000382 | 262910320 | 4300037223 | 15501296 | COP.01EB125MGR | CYL ROLL BRG 01 B 125M GR COOPER | 2026-05-12 | 2026-06-22 | EMWH | 1 | 1 | 100% | 1048.87 | 1048.87 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0002A | 26Z0000383 | 262910319 | 4300037815 | 15419258 | H 3140 | BRG BUSHING FIXAT 180MM H 3140 SKF | 2026-05-12 | 2026-07-22 | EMWH | 2 | 2 | 100% | 201.25 | 402.5 | 0000000 | SHS | 71 | 05/2026 | 08/2026 | 0 | F66050 |  | ✘ |  | 25.06.2026 ETA - SANR0409719
0008A | 26Z0000383 | 262910319 | 4300037815 | 17510662 | 70X90X10 HMSA10 RG | NBR SEAL RETAINER 70MM 90MM | 2026-05-12 | 2026-06-22 | EMWH | 12 | 12 | 100% | 1.89 | 22.68 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0009A | 26Z0000383 | 262910319 | 4300037815 | 15722015 | 32311 | ROLL BEARING 32311 SKF | 2026-05-12 | 2026-06-22 | TBEW | 6 | 6 | 100% | 28.27 | 169.62 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 - ETA - SANR0409719
0010A | 26Z0000383 | 262910319 | 4300037815 | 13065480 | FRB 10/320 | LOCATING RING FRB 10/320 SKF | 2026-05-12 | 2026-06-22 | EMWH | 8 | 8 | 100% | 12.87 | 102.96 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0001A | 26Z0000304 | 262910137 |  |  | QJ 228 N2MA | ANGULAR CONTACT BALL BEARING QJ 228 N2MA | 2026-04-17 | 2026-07-01 | EMWH | 2 | 2 | 100% | 947.6 | 1895.2 | 0000000 | SHS | 75 | 04/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 05.06.2026 - ETA - SANR0409714
0002A | 26Z0000291 | 262910021 | 4300036955 | 15004591 | 22328 CCJA/W33VA405 | BEARING 22328 CC JA C4 W33 VA405 SKF | 2026-04-09 | 2026-07-01 | EMWH | 37 | 37 | 100% | 838.97 | 31041.89 | 12764 | READY FOR COLLECTION | 83 | 04/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0002C | 26Z0000291 | 262910021 | 4300036955 | 15004591 | 22328 CCJA/W33VA405 | BEARING 22328 CC JA C4 W33 VA405 SKF | 2026-04-09 | 2026-07-01 | EMWH | 33 | 33 | 100% | 838.97 | 27686.01 | 12764 | READY FOR COLLECTION | 83 | 04/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0009A | 26Z0000291 | 262910021 | 4300036955 | 13188470 | COP.01EB140MGR | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-04-09 | 2026-07-01 | EMWH | 2 | 2 | 100% | 1449.22 | 2898.44 | 12764 | READY FOR COLLECTION | 83 | 04/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 2026-06-09 - SKF informed that it is available for collection.
0001A | 26Z0000279 | 252912134 | 4300034374 | 15056773 | 32230 | BEARING;TAPERED ROLLER;32230JR;KOYO | 2026-04-01 | 2026-06-10 | EMWH | 10 | 10 | 100% | 478.59 | 4785.9 | 12755 | COLLECTED | ✔ OK | 04/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0001B | 26Z0000410 | 262910450 | 4300038547 | 17563131 | CMSS 943-LCI-SY-20M | CABLE ASSEMBLY; CMSS 943-LCI-SY-20M; SKF | 2026-05-21 | 2026-06-16 | EMWH | 20 | 20 | 100% | 192.03 | 3840.6 | 12739 | COLLECTED | ✔ OK | 05/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0002A | 26Z0000410 | 262910450 | 4300038547 | 17563129 | CMSS 942-LCI-SY-20M | CABLE ASSEMBLY; CMSS 942-LCT-SY-20M; SKF | 2026-05-21 | 2026-06-18 | EMWH | 50 | 50 | 100% | 138.68 | 6934 | 12751 | COLLECTED | ✔ OK | 05/2026 | OK | 0 | F66050 | 2026-06-02 | ✔ | 2026-06-22
0003A | 26Z0000381 | 262910321 | 4300037783 | 15055680 | 22226 EK/C3 | BEARING 22226 CCK W33 SKF | 2026-05-12 | 2026-06-22 | EMWH | 15 | 15 | 100% | 308.44 | 4626.6 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0004A | 26Z0000381 | 262910321 | 4300037783 | 15153017 | 6316/C3 | BEARING 6316-C3;FRAME 250S/M;WEG | 2026-05-12 | 2026-06-22 | EMWH | 1 | 1 | 100% | 46.04 | 46.04 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0005A | 26Z0000381 | 262910321 | 4300037783 | 15056773 | 32230 | BEARING;TAPERED ROLLER;32230JR;KOYO | 2026-05-12 | 2026-06-22 | EMWH | 10 | 10 | 100% | 492.38 | 4923.8 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
0006A | 26Z0000381 | 262910321 | 4300037783 | 15153017 | 6316/C3 | BEARING 6316-C3;FRAME 250S/M;WEG | 2026-05-12 | 2026-06-22 | EMWH | 2 | 2 | 100% | 46.04 | 92.08 | 0000000 | SHS | 41 | 05/2026 | 07/2026 | 0 | F66050 |  | 🔮 |  | 25.06.2026 ETA - SANR0409719
| 26Z0000474 | 262910597 | 4300039614 | 13285590 | 24144CC/W33 | SPHERICAL ROLLER BEARING, 24144CC/W33 | 2026-06-12 | 2026-07-22 | EMWH | 3 | 3 | 100% | 1875.16 | 5625.48 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 | 15156745 | 22248CC/W33 | SPHERICAL ROLLER BEARING, 22248CC/W33 | 2026-06-12 | 2026-07-22 | EMWH | 1 | 1 | 100% | 1909.89 | 1909.89 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | SI 20E SKF | FEMALE ROD END BEARING, SI 20E SKF | 2026-06-12 | 2026-07-22 | EMWH | 4 | 4 | 100% | 26.11 | 104.44 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | BUSH-5040 110 | TAPER BUSHING 5040 X 110 MM | 2026-06-12 |  | EMWH | 1 |  | 0% | 75.01 | 75.01 | 0000000 | ENT | TBA | 06/2026 |  | 1 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | BUSH-4545 90 | TAPER BUSHING 4545 X 90 MM | 2026-06-12 | 2026-07-22 | EMWH | 1 | 1 | 100% | 75.01 | 75.01 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
|  | 262910597 | 4300039614 |  | LSM200BRTTIM | SPLIT CYLINDRICAL ROLLER BEARING, LSM200 | 2026-06-12 |  |  | 1 |  | 0% | 5823.9 | 5823.9 | 0000000 | ENT | TBA | 06/2026 |  | 1 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | SI 20E SKF | FEMALE ROD END BEARING, SI 20E SKF | 2026-06-12 | 2026-07-22 | EMWH | 4 | 4 | 100% | 26.11 | 104.44 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
|  | 262910597 | 4300039614 |  | MSM170HRTL | LABYRINTH SEAL RING, MSM170HRTL | 2026-06-12 |  |  | 2 |  | 0% | 131.38 | 262.76 | 0000000 | ENT | TBA | 06/2026 |  | 2 | F66050 |  | ✘
|  | 262910597 | 4300039614 |  | SD32 TIMKEN | SPLIT PLUMMER BLOCK HOUSING, SD32 | 2026-06-12 |  |  | 2 |  | 0% | 2618.87 | 5237.74 | 0000000 | ENT | TBA | 06/2026 |  | 2 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | NU 2203 ECP | SG ROW CYLIND. ROLLER BEARING, NU 2203 | 2026-06-12 | 2026-07-22 | EMWH | 2 | 2 | 100% | 20.8 | 41.6 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | 6007-RS1 SKF | SG ROW DEEP GROOVE BALL BEARING, 6007 | 2026-06-12 | 2026-07-22 | EMWH | 2 | 2 | 100% | 3.57 | 7.14 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | 6309 C3 SKF | SG ROW DEEP GROOVE BALL BEARING, 6309 | 2026-06-12 | 2026-07-22 | EMWH | 10 | 10 | 100% | 7.61 | 76.1 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | 6009 Z SKF | SG ROW DEEP GROOVE BALL BEARING, 6009 | 2026-06-12 | 2026-07-22 | EMWH | 2 | 2 | 100% | 6.72 | 13.44 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 | 15506080 | 23038 CC W33 | SPHERICAL ROLLER BEARING, 23038 CC W33 | 2026-06-12 | 2026-07-22 | EMWH | 11 | 11 | 100% | 627.61 | 6903.71 | 0000000 | ENT | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | ETS 44 SKF¦1 | END CR FOR PLUMMER BLOCK HOUSING, ETS 44 | 2026-06-12 | 2026-07-22 | EMWH | 2 | 2 | 100% | 85.56 | 171.12 | 0000000 | ALL | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 | 13285590 | 24144 CC/W33 | SPHERICAL ROLLER BEARING, 24144CC/W33 | 2026-06-12 | 2026-07-22 | EMWH | 5 | 5 | 100% | 1875.16 | 9375.8 | 0000000 | ENT | 40 | 06/2026 | 08/2026 | 0 | F66050 |  | ✘
|  | 262910597 | 4300039614 |  | 31181602-SKF | V-RING SEAL, 31181602-SKF | 2026-06-12 |  |  | 10 |  | 0% | 76.27 | 762.7 | 0000000 | ENT | TBA | 06/2026 |  | 10 | F66050 |  | ✘
| 26Z0000474 | 262910597 | 4300039614 |  | 220 VA | V-RING SEAL, 220 VA | 2026-06-12 |  | EMWH | 10 |  | 0% | 107.1 | 1071 | 0000000 | ENT | TBA | 06/2026 |  | 10 | F66050 |  | ✘
|  | 262910597 | 4300039614 |  | MSM170HRTL | LABYRINTH SEAL RING, MSM170HRTL | 2026-06-12 |  |  | 2 |  | 0% | 131.38 | 262.76 | 0000000 | ENT | TBA | 06/2026 |  | 2 | F66050 |  | ✘
|  |  | 4300038757 | 13188470 |  | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-16 |  |  | 1 |  | 0% | 2012.81 | 2012.81 | 0000000 | ENT | TBA | 05/2026 |  | 1 | F66050 |  | ✘
|  |  | 4300038757 | 16177612 |  | SEAL TSN526S SKF | 2026-05-16 |  |  | 12 |  | 0% | 157.26 | 1887.12 | 0000000 | ENT | TBA | 05/2026 |  | 12 | F66050 |  | ✘
|  |  | 4300038757 | 16177612 |  | SEAL TSN526S SKF | 2026-05-16 |  |  | 4 |  | 0% | 157.26 | 629.04 | 0000000 | ENT | TBA | 05/2026 |  | 4 | F66050 |  | ✘
|  |  | 4300038757 | 16177612 |  | SEAL TSN526S SKF | 2026-05-16 |  |  | 16 |  | 0% | 157.26 | 2516.16 | 0000000 | ENT | TBA | 05/2026 |  | 16 | F66050 |  | ✘
|  |  | 4300038757 | 13040555 |  | CYL ROLL BRG MSM180BR TIMKEN | 2026-05-16 |  |  | 2 |  | 0% | 5933.52 | 11867.04 | 0000000 | ENT | TBA | 05/2026 |  | 2 | F66050 |  | ✘
|  |  | 4300038757 | 13040555 |  | CYL ROLL BRG MSM180BR TIMKEN | 2026-05-16 |  |  | 5 |  | 0% | 5933.52 | 29667.6 | 0000000 | ENT | TBA | 05/2026 |  | 5 | F66050 |  | ✘
|  |  | 4300038757 | 16177612 |  | SEAL TSN526S SKF | 2026-05-16 |  |  | 16 |  | 0% | 157.26 | 2516.16 | 0000000 | ENT | TBA | 05/2026 |  | 16 | F66050 |  | ✘
|  |  | 4300038757 | 15055680 |  | BEARING 22226 CCK W33 SKF | 2026-05-16 |  |  | 4 |  | 0% | 416.4 | 1665.6 | 0000000 | ENT | TBA | 05/2026 |  | 4 | F66050 |  | ✘
|  |  | 4300038757 | 13188470 |  | CL RL BRG 01 B 140M GR COOPER BEARINGS | 2026-05-16 |  |  | 1 |  | 0% | 2012.81 | 2012.81 | 0000000 | ENT | TBA | 05/2026 |  | 1 | F66050 |  | ✘
|  |  | 4300038757 | 15419258 |  | BRG BUSHING FIXAT 180MM H 3140 SKF | 2026-05-16 |  |  | 2 |  | 0% | 271.69 | 543.38 | 0000000 | ENT | TBA | 05/2026 |  | 2 | F66050 |  | ✘
|  |  |  | 17564039 |  | V,RING SEAL 190X210X25-PN 31181602-SKF | 2026-09-06 | 2026-08-06 |  | 10 |  | 0% | 10.68 | 106.8 |  | BUDGET | -31 | 09/2026 | 08/2026 | 10 | F66050 |  |  |  | 09-06-2026 - Vulcan's request for a quote on the items (sent to Mel) - Naftal Bute
|  |  |  | 17564042 |  | SEAL, RING;V,V-RING SEAL, DESIGN VA190 | 2026-09-06 | 2026-07-30 |  | 10 |  | 0% | 70.12 | 701.2 |  | BUDGET | -38 | 09/2026 | 08/2026 | 10 | F66050 |  |  |  | 09-06-2026 - Vulcan's request for a quote on the items (sent to Mel) - Naftal Bute
|  |  |  | 17564043 |  | 220 VA V V-RING SEAL, VA DESIGN-SKF | 2026-09-06 | 2026-07-30 |  | 10 |  | 0% | 107.1 | 1071 |  | BUDGET | -38 | 09/2026 | 08/2026 | 10 | F66050 |  |  |  | 09-06-2026 - Vulcan's request for a quote on the items (sent to Mel) - Naftal Bute
|  |  |  | 15719798 |  | V RING CR401706 SKF | 2026-09-06 | 2026-07-30 |  | 40 |  | 0% | 162.71 | 6508.4 |  | BUDGET | -38 | 09/2026 | 08/2026 | 40 | F66050 |  |  |  | 09-06-2026 - Vulcan's request for a quote on the items (sent to Mel) - Naftal Bute
|  |  |  | 15430120 |  | BEARING UNIT SQUARE FLANGED | 2026-09-06 |  |  | 2 |  | 0% |  | 0 |  | BUDGET | TBA | 09/2026 |  | 2 | F66050 |  |  |  | 09-06-2026 - Item not quoted by SKF (no accurate item description)
|  |  |  | 15055364 | 22222-E1A-M-C3 | BEARING 22222-E1A-M-C3 FAG | 2026-09-06 | 2026-07-09 |  | 20 |  | 0% | 157.7 | 3154 |  | BUDGET | -59 | 09/2026 | 07/2026 | 20 | F66050 |  |  |  | 09-06-2026 - Vulcan's request for a quote on the items (sent to Mel) - Naftal Bute
|  |  |  | 17564395 | 6300-2Z-SKF | BALL BEARING-DEEP GROOVE-REF 6300-2Z-SKF | 2026-09-06 | 2026-07-09 |  | 30 |  | 0% | 1.94 | 58.2 |  | BUDGET | -59 | 09/2026 | 07/2026 | 30 | F66050 |  |  |  | 09-06-2026 - Vulcan's request for a quote on the items (sent to Mel) - Naftal Bute
|  |  |  | 17511563 | 22344 EJW33W | ROLAMENTO 22344 EJW33W45A TIMKEN | 2026-09-06 | 2026-08-28 |  | 4 |  | 0% | 3583.87 | 14335.48 |  | BUDGET | -9 | 09/2026 | 09/2026 | 4 | F66050 |  |  |  | 09-06-2026 - Vulcan's request for a quote on the items (sent to Mel) - Naftal Bute

## 🔍 LOOKUP
🔍 QUICK ORDER LOOKUP
| SEARCH TYPE | ← CODE / NUMBER (Type here)
| SKF Order | 26Z0000386 | [7 empty] | 26Z0000386
📋 ORDER IDENTIFICATION
| Line | SKF Order | TATA Order | Vulcan PO | Warehouse | Order Date | SKF Delivery Date | Days
| 0001A | 26Z0000386 | 262910319A | 4300037815 | EMWH | 2026-05-13 | 2026-06-09 | ✔ OK
| Invoice No. | Status | Month/Year | Unit Price | Qty Ordered | Qty Shipped | Qty Pending | SKF Designation
| 12675 | COLLECTED | 05/2026 | 678.04 | 20 | 20 | OK | 22326 CCJA/W33VA405
██████████████████████████████ 100% expedido
💰 LINE TOTAL (USD)
13560.8
✔ CUSTOMER DELIVERY
| Delivery Status | SKF Collection Date |  | Customer Delivery Date |  | Notes
| 2026-05-22 | F66050 |  | ✔ |  | 2026-06-08
📦 ORDER ITEMS
| # | Line | SKF Designation |  | Warehouse | Qty Ord. | Qty Shp. | Status | Days
💡 Tipo (B4): SKF Order ¦ TATA Order ¦ Vulcan PO ¦ Invoice No. → Código em C4 → Lista de itens atualiza automaticamente

## 📊 DASHBOARD
📊 TATA — MANAGEMENT DASHBOARD
Values calculated automatically from the ORDERS sheet
| 💰 TOTAL VALUE |  | 📦 LINES |  | ✅ QTY SHIPPED |  | ⏳ QTY PENDING |  | 📈 % SHIPPED | ✔ DELIVERED CUST.
| 582941.25 |  | 135 |  | 1178 |  | 265 |  | 81.64% | 50
📅 DUE THIS MONTH
| 📦 Lines |  | 💰 Value |  | ⏳ Pending |  | ✅ Shipped
| 54 |  | 126672.71 |  | 3 |  | 428
📌 STATUS SUMMARY
| Status | Description | Lines | Qty Ord. | Qty Shp. | Qty Pend. | Value (USD) | Delivered
| COLLECTED | Collected | 65 | 544 | 544 | 0 | 127412.47 | 50
| READY FOR COLLECTION | Ready for Collection | 14 | 112 | 112 | 0 | 63773.98 | 0
| SHS | Shipped (SHS) | 38 | 254 | 251 | 3 | 153391.43 | 0
| BOK | Reserved (BOK) | 3 | 7 | 7 | 0 | 258.3 | 0
| RBK | Re-reserved (RBK) | 4 | 188 | 188 | 0 | 37416.3 | 0
| ENT | Entry (ENT) | 21 | 135 | 16 | 119 | 88432.53 | 0
| RPI | Re-planned (RPI) | 9 | 46 | 29 | 17 | 78192.5 | 0
| ALL | Allocated (ALL) | 10 | 31 | 31 | 0 | 8128.66 | 0
| BUDGET | Request a quote | 8 | 126 | 0 | 126 | 25935.08 | 0
| TOTAL |  | 172 | 1443 | 1178 | 265 | 582941.25 | 50
🏭 WAREHOUSE CONTROL
| Code | Description | Lines | Qty Ordered | Qty Shp. | Qty Pend. | % Shp. | Value (USD)
| EMWH | Europe Distribution Center | 131 | 1167 | 1111 | 56 | 95.2% | 471131.92
| QZSS | South Africa Warehouse | 11 | 24 | 21 | 3 | 87.5% | 13159.19
| TBEW | Belgium Warehouse | 6 | 36 | 36 | 0 | 100% | 1406.68
| II01 | International Warehouse | 1 | 10 | 10 | 0 | 100% | 3640.8
🧾 INVOICE CONTROL
| Situation | No. of Lines | Qty Ordered | Qty Shp. | Value (USD) | % of Total
| Invoiced | 672 | 1443 | 1178 | 582941.25 | 69.29%
| Not Invoiced | 85 | 661 | 522 | 365819.72 | 30.71%
✔ CUSTOMER DELIVERY CONTROL
| Situation | No. of Lines | No. of Items | Value (USD) | % Lines | % Value
| ✔ Delivered to Customer | 50 | 470 | 116066.92 | 37.04% | 19.91%
| ✘ Not Delivered | 62 | 416 | 282576.65 | 45.93% | 48.47%
| 📦 With SKF Collection | 172 | 1178 | 582941.25 | 127.4% | 100%
| ⚠ Attention | 15 | 74 | 11345.55 | 11.11% | 1.946%
| 📅 Current Month Forecast | 0 | 0 | 0 | 0% | 0%
| 🔮 Forecast for Next Month | 37 | 218 | 147017.05 | 27.41% | 25.22%
| No Record | -29 | 0 | 25935.08 | -21.48% | 4.449%
📅 CONTROL — SKF COLLECTION DATE vs CUSTOMER DELIVERY
| Situation | No. of Lines | No. of Items | % Lines | Note
| 📦 With SKF Collection registered | 172 | 1178 | 127.4% | Collection confirmed in system
| ✔ Delivered to Customer | 50 | 470 | 37.04% | Marked as delivered
| ⚠ Attention | 15 | 74 | 11.11% | Marked as attention
| 📅 Current Month Forecast | 0 | 0 | 0% | Forecast for current month
| 🔮 Forecast for Next Month | 37 | 218 | 27.41% | Forecast for next month
| 🔗 SKF Collection + Customer Delivery | 50 | 470 | 37.04% | Both registered
| ⏳ Collected — awaiting customer delivery | 122 | 708 | 90.37% | Collection OK, delivery pending
| ❌ No SKF Collection registered | -37 | 0 | -27.41% | Awaiting SKF collection

## 📈 CHARTS (hidden)
📈 TATA — MANAGEMENT CHARTS
F66050 – TATA ¦ 02/06/2026
| TOTAL VALUE | LINES | QTY SHIPPED | QTY PENDING | % SHIPPED | DELIVERED CUST.
| 582941.25 | 135 | 1178 | 265 | 81.64% | 50
[7 empty] | Status | Value | Qty Ordered | Qty Shipped
[7 empty] | Collected | 39880.96 | 102 | 102
[7 empty] | Ready for Collection | 64621.08 | 363 | 363
[7 empty] | Shipped (SHS) | 112760.36 | 272 | 272
[7 empty] | Reserved (BOK) | 129525.37 | 72 | 0
[7 empty] | Re-reserved (RBK) | 61501.8 | 110 | 0
[7 empty] | Entry (ENT) | 39369.66 | 218 | 0
[7 empty] | Re-planned (RPI) | 13852.11 | 31 | 0
[7 empty] | Allocated (ALL) | 869.54 | 10 | 0
[7 empty] | Warehouse | Value | Qty Ord | Qty Shp
[7 empty] | EMWH — Europe Distribution Center | 444174.21 | 1108 | 684
[7 empty] | II01 — International Warehouse | 3640.8 | 10 | 10
[7 empty] | QZSS — South Africa Warehouse | 13159.19 | 24 | 7
[7 empty] | TBEW — Belgium Warehouse | 1406.68 | 36 | 36
[7 empty] | Situation | Qtd
[7 empty] | Shipped | 737
[7 empty] | Pending | 441
[7 empty] | Situation | Qtd
[7 empty] | SKF Collected | 135
[7 empty] | Customer Delivery | 0
[7 empty] | No Collection/Delivery | 0

## 🔄 STATUS CONTROL
🔄 DETAILED STATUS CONTROL
⚡ Updated automatically via COUNTIF/SUMIF from ORDERS sheet
Status | Description | Lines | Qty Ordered | Qty Shp. | Qty Pend. | % Shp. | Value (USD) | Cust. Del. | SKF Collected
COLLECTED | Collected | 65 | 544 | 544 | 0 | 100% | 127412.47 | 50 | 65
READY FOR COLLECTION | Ready for Collection | 14 | 112 | 112 | 0 | 100% | 63773.98 | 0 | 14
SHS | Shipped (SHS) | 38 | 254 | 251 | 3 | 98.82% | 153391.43 | 0 | 38
BOK | Reserved (BOK) | 3 | 7 | 7 | 0 | 100% | 258.3 | 0 | 3
RBK | Re-reserved (RBK) | 4 | 188 | 188 | 0 | 100% | 37416.3 | 0 | 4
ENT | Entry (ENT) | 21 | 135 | 16 | 119 | 11.85% | 88432.53 | 0 | 21
RPI | Re-planned (RPI) | 9 | 46 | 29 | 17 | 63.04% | 78192.5 | 0 | 9
ALL | Allocated (ALL) | 10 | 31 | 31 | 0 | 100% | 8128.66 | 0 | 10
BUDGET | Request a quote | 8 | 126 | 0 | 126 | 0 | 25935.08 | 0 | 0
TOTAL |  | 172 | 1443 | 1178 | 265 | 81.64% | 582941.25 | 50 | 164

## 📅 MONTHLY
📅 MONTHLY ANALYSIS — Calculated automatically
⚡ Edit B and C to adjust periods.
Month/Year | Start Date | End Date | No. Lines | Qty Ordered | Qty Shp. | Qty Pend. | % Shp. | Value (USD)
12/2025 | 2025-12-01 | 2025-12-31 | 2 | 4 | 4 | 0 | 100% | 8374.13
02/2026 | 2026-02-01 | 2026-02-28 | 30 | 117 | 116 | 1 | 99.15% | 29106.23
03/2026 | 2026-03-01 | 2026-03-31 | 21 | 205 | 205 | 0 | 100% | 11058.87
04/2026 | 2026-04-01 | 2026-04-30 | 28 | 279 | 265 | 14 | 94.98% | 167876.99
05/2026 | 2026-05-01 | 2026-05-31 | 64 | 637 | 541 | 96 | 84.93% | 302685.91
06/2026 | 2026-06-01 | 2026-06-30 | 19 | 75 | 47 | 28 | 62.67% | 37904.04
08/2026 | 2026-08-01 | 2026-08-31 | 0 | 0 | 0 | 0 | 0% | 0
11/2026 | 2026-11-01 | 2026-11-30 | 0 | 0 | 0 | 0 | 0% | 0
03/2027 | 2027-03-01 | 2027-03-31 | 0 | 0 | 0 | 0 | 0% | 0
08/2027 | 2027-08-01 | 2027-08-31 | 0 | 0 | 0 | 0 | 0% | 0
02/2028 | 2028-02-01 | 2028-02-29 | 0 | 0 | 0 | 0 | 0% | 0
TOTAL |  |  | 164 | 1317 | 1178 | 139 | 89.45% | 557006.17

## 📄 INVOICE CONTROL (hidden)
📄 INVOICE CONTROL — Calculated automatically from ORDERS sheet
⚡ Updated automatically — each row = one unique Invoice Nº from column Q of ORDERS sheet (excluding 0000000)
Invoice Nº | Nº Lines | TATA Order | Vulcan Order (PO) | Total USD | Status | Days to Delivery | SKF Collection Date | Delivered to Customer | Customer Delivery Date
12568 | 1 |  |  | 455.12
12611 | 1 |  |  | 533.32
12660 | 1 |  |  | 4883.5
12612 | 1 |  |  | 1831.7
12403 | 1 |  |  | 1048.88
12452 | 1 |  |  | 7325.25
12545 | 0 |  |  | 0
12632 | 0 |  |  | 0
12723 | 0 |  |  | 0
12622 | 0 |  |  | 0
12661 | 0 |  |  | 0
12431 | 0 |  |  | 0
12755 | 0 |  |  | 0
12675 | 0 |  |  | 0
12562 | 0 |  |  | 0
12720 | 0 |  |  | 0
12610 | 0 |  |  | 0
12679 | 0 |  |  | 0
12643 | 0 |  |  | 0
12721 | 0 |  |  | 0
12722 | 0 |  |  | 0
12613 | 0 |  |  | 0
12739 | 0 |  |  | 0
12751 | 0 |  |  | 0
⚡ TOTAL — updates automatically |  |  |  | 16077.77